Event Plan

|  |  |
| --- | --- |
| Tuesday Afternoon | Setup Shermann PA & Amplifier  Setup Mic Stands with Mics & Cables  Prepare Stage End of Multicore  Prepare Lights with DMX addresses |
| Tuesday Evening | Rehersal / Sound Checks |
| Thursday Evening | Rig Stage Bar Lights, DMX and Power – Test  Put Canvas On Screen |
| Friday Morning / Afternoon | Setup Control Desk  Run DMX and Snake Wires in Hall  Run VGA Cable  Setup LED Uplighters  Setup Band Dis and Mics  Fix Curtain Runners  Setup Stage Projector – Adjust to fit  Setup Rear Projector  Rig Stage Bar Lights  Focus / Reposition Lights |
| Friday Evening | BB Coffee Morning Setup – Move Desk out of way |
| Saturday Morning | BB Coffee Morning |
| Saturday Afternoon | Chairs in Hall  SOUND CHECK 1PM  Final Technical Checks |
| Saturday Evening | EVENT |
| Sunday | DERIG |